## Project Timeline
Hyperledger- Automated Programming |  |  |  |  | June | July | August | September | October | November
| Milestone | Description | Sub-tasks | Deliverables
| Short Term Plan |  | Continue with Furioos
1 | Research | The first month of the project will be spent performing extensive research and acquiring a complete grasp of the existing environment of automated programming for smart contracts. | Collect Research papers/articles | Literature review report summarizing key findings and relevant research papers.
Conduct in-dept lit. review
Analyze existing approaches and tools
2 | Technical Feasibility | The major focus of the project's second month is on investigating the technical viability of automated chaincode programming in Hyperledger Fabric. | Evaluate different approaches of developing SC | Evaluation report of the experimentation with representative examples.
Experiment different approaches
3 | Selection and Design | The focus of the third month of the project is on identifying a viable technique for automated chaincode programming in Hyperledger Fabric and developing a chaincode specification style. | Select suitable approach | Documentation of the selected automated programming approach for Hyperledger Fabric. Evaluation criteria document defining the metrics and criteria for assessing the effectiveness of the automated programming approach.
Formulating chaincode specification style
Define evaluation criteria
4 | Implementation and Testing | The focus of the fourth month of the project is on implementing the chosen automated programming technique for Hyperledger Fabric chaincode and undertaking extensive testing. | Implement the automated programming approach | Test results report summarizing the outcomes of extensive testing conducted on the implemented approach.
Experiment devloping SC
Conduct extensive testing
5 | Documentation and Evaluation | During the fifth and final month of the project, the focus is on evaluating the automated programming approach implemented for Hyperledger Fabric chaincode and documenting the findings. | Document the findings | Evaluation report assessing the effectiveness, accuracy, and performance of the automated programming approach compared to manual development.
|  |  | Create Project report | [7 empty] | Float
Notes: 1. Every activity starts with brainstorming the goals and what questions will be addressed by the task 2. Each monthly activity starts with a list of questionnaire which will be addressed during the monthly activities. 3. On closure of each milestone, monthly activities should be evaluayted witht the team.